## Gantt Chart
GANTT CHART
| PROJECT TITLE | SBMS Monitoring System for Human Positioning using Smartphones |  |  |  |  | COMPANY NAME | [10 empty] | Nippon Koei
| Supervisor | Professor Lawrence |  |  |  |  | DATE | [10 empty] | 2021-09-23
[18 empty] | September | [32 empty] | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Mon | Tue | Wed | Thur
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Project Definition and Planning
1.1 | Identify User Needs | Everyone | 2021-09-16 | 2021-09-17 | 1 | 100% | bar: Thur 16
1.2 | Identify Requirement | Everyone | 2021-09-17 | 2021-09-18 | 1 | 100% | bar: Sat 18
1.3 | Identify Stakeholders | Everyone | 2021-09-18 | 2021-09-18 | 0 | 100% | bar: Sat 18
1.4 | Preparation for Requirement Gathering | Everyone | 2021-09-20 | 2021-09-23 | 3 | 100% | bar: Mon 20
1.5 | Requirement Gathering | Everyone | 2021-09-23 | 2021-09-23 | 0 | 100% | bar: Thur 23
1.6 | Research on Human Positioning Technology | Everyone | 2021-09-27 | 2021-09-30 | 3 | 100% | bar: Mon 27
2 | Design
2.1 | Scope & Goal Setting | Everyone | 2021-10-01 | 2021-10-03 | 2 | 100% | bar: Fri 1
2.2 | Use Cases & Use Case Diagram | Dai Yu | 2021-10-04 | 2021-10-06 | 2 | 100% | bar: Mon 4
2.3 | Gantt Chart | Dai Yu | 2021-10-07 | 2021-10-09 | 2 | 100% | bar: Thur 7
2.4 | Flow Chart | Dai Yu | 2021-10-11 | 2021-10-13 | 2 | 100% | bar: Mon 11
2.5 | Roadmap | Dai Yu | 2021-10-14 | 2021-10-18 | 4 | 100% | bar: Thur 14
2.6 | Finalize Wireless Technology | Brendan | 2021-10-18 | 2021-10-21 | 3 | 80% | bar: Mon 18
2.7 | Proposal for Human Positioning Technology | Everyone | 2021-10-18 | 2021-10-21 | 3 | 50% | bar: Fri 22
2.8 | Preparation for Customer Day | Everyone | 2021-10-22 | 2021-10-28 | 6 | 100% | bar: Fri 22
2.9 | Customer Day 1 | Everyone | 2021-10-28 | 2021-10-28 | 0 | 100%
3 | Development
3.1 | Status & Tracking | Abadi | 2021-09-23 | 2022-01-31 | 128 | 0%
3.2 | Developing of A.4. Project
3.2.1 | Setting up of Dummy Data | Brendan | 2021-10-29 | 2021-11-12 | 13 | 0%
3.2.1 | Setting up of Floor Plan | Taufik | 2021-10-29 | 2021-11-12 | 13 | 0%
3.2.3 | Setup positioning technology | Karin | 2021-11-12 | 2021-12-07 | 25 | 0%
3.2.4 | Work on data visualisation on heatmap | Daiyu | 2021-12-07 | 2022-01-31 | 54 | 0%
3.2.5 | Work on counting of users based on user entry into the room | Abadi | 2021-12-07 | 2022-01-31 | 54 | 0%
3.3 | Github Updates | Karin | 2021-09-23 | 2022-01-31 | 128 | 0%
3.3.1 | Gantt Chart Updates | Dai Yu | 2021-09-23 | 2022-01-31 | 128 | 0%
4 | Project Performance/Monitoring/Testing
4.1 | Project Objectives |  | 2021-09-23 | 2021-09-23 | 0 | 0%
4.2 | Quality Deliverables |  | 2021-09-23 | 2021-09-23 | 0 | 0%
4.3 | User Acceptance Testing (UAT) |  | 2021-09-23 | 2021-09-23 | 0 | 0%
4.4 | System Integration Testing (SIT) |  | 2021-09-23 | 2021-09-23 | 0 | 0%
4.5 | Final Report |  | 2021-09-23 | 2021-09-23 | 0 | 0%
4.6 | Final Documentation |  | 2021-09-23 | 2021-09-23 | 0 | 0%
100%
50%